## Sheet1
|  |  |  | Today |  | Camera Stream on computer |  |  |  |  | Hardware Complete
Task | Lead | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | NAMES
Hardware | [14 empty] | AH | Adam Harper
Camera | AH | [13 empty] | CL | Celina Luckevich
Research cameras | AH | Week 1: 100 | JM | Joseph Mahoney
Order Camera | AH | Today Week 3: 0 | JW | Joshua Warren
Connect to network | AH | Camera Stream on computer Week 5: 0
View video stream on app | AH | Camera Stream on computer Week 5: 100
View video stream on comp | AH | Camera Stream on computer Week 5: 50
Driving Robots | JW
Obtain parts (incluing MCUs) | JW | Today Week 3: 100
Build/Test H-bridge circuits | JW | Today Week 3: 100
Test driving robots with MCU | JW | Today Week 3: 50
Ultrasonic Sensor | CL
Obtain parts | CL | Today Week 4: 0
Build circuit to connect to MCU | CL | Today Week 4: 0
Test circuit | CL | Camera Stream on computer Week 6: 0
Robot Arms | JM
Design arms | JW | Camera Stream on computer Week 5: 10
Design and build flags | JW | Camera Stream on computer Week 6: 0
Build circuit for servo to MCU | JM | Camera Stream on computer Week 8: 0
Test circuit | JM | Camera Stream on computer Week 9: 0
Test arms | JM | Camera Stream on computer Week 9: 0
|  |  |  | Today |  |  |  | Detect Objects |  | GUI Done |  | Find all flags
Task | Lead | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Software
Drive Rover using OpenCV | CL
Research OpenCV | CL | Week 1: 100
Recognize Objects | CL | Today Week 4: 25
Determine how to avoid them | CL | Detect Objects Week 8: 0
Send instructions to MCUs | AH | GUI Done Week 10: 0
GUI | AH
Design Layout | AH | Today Week 3: 100
Write Code | AH | Today Week 4: 90
Debug Code | AH | Today Week 5: 90
Display video feeds | AH | Detect Objects Week 8: 10
Improve Aesthetics | AH | Find all flags Week 13: 0
MCUs | JW
Build Program Flowchart | JW | Week 1: 100
Write Code | JW | Today Week 3: 60
Debug Code | JW | Today Week 4: 20
Integrate with robots | JW | Detect Objects Week7: 0
Robots work coop/compet | JM
Find all flags | JM | GUI Done Week 10: 0
Race to get most | JM | Find all flags Week 11: 0
Optimize Performance | JM | Find all flags Week 12: 0